## General_1 (hidden)
Nro | Tipo | Nombre | Descripcion | Marca | Prioridad | Desarrollador | Lider desarrollo | Complejidad QA | QA responsable | Avance Total | %correcto | Nro de casos | Correctos | Fallados | Postergado | Bloqueados | Por hacer | Fecha inicial | Fecha final | COMENTARIOS
1 | MEJ | Mejora en reporte ventas por vendedor – monto total IGV |  | Ambas |  | Eder Acate | Breisner Lopez | Bajo | Veronica | 100% | 100% | 5 | 5 | 0 | 0 | 0 | 0 | 2021-01-15 | 2021-01-22 | 15/01/2021: Se culmino el entendimiento
2 | PROY | Proyecto Multimarca |  | Ambas |  | Jesus Inca | Alessandro Gallirgos |  | Vero/Jennif/Yo | #REF! | #REF! | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | 2021-01-15 | 2021-01-21 | 21/01/2021: Se tiene 5 casos Fallados por el defecto 6 (Para NO FID , Esta guardando como null),1 mejora (Esta visualizandose el nombre de la razon social Mifarma en los comprobantes).
3 | INC | Correccion descuadro de totales en pago delivery convenio |  | Ambas |  | Ivan Coronado | Breisner Lopez | Alto | Jennifer | 0% | 0% | 5 | 0 | 0 | 0 | 5 | 0 | 2021-01-15 | 2021-01-22 | 20/01 Se tiene bloqueado por error de convenios.
4 | INC | Correccion voucher de pago con tarjeta sale sin fecha |  | Inkafarma |  | Ivan Coronado | Breisner Lopez | NA | Brian | NA | NA | NA | NA | NA | NA | NA | NA | 2021-01-15 | 2021-01-22 | No aplica
5 | MEJ | Anulación de cheques según los puntos disponibles del cliente FID |  | Inkafarma |  | Eder Acate | Breisner Lopez | NA | Yoselin | NA | NA | NA | NA | NA | NA | NA | NA | 2021-01-15 | 2021-01-22
6 | MEJ | Mejoras PAP |  | Ambas |  | Ederson Montesinos | Ederson Montesinos |  | Yoselin | 100% | 100% | 9 | 9 | 0 | #REF! | #REF! | 0 | 2021-01-21 | 2021-01-22 | 15/01/2021 Se culminó análisis y elaboración de querys para los ambientes Mifarma, Inkafarma, RAC. 18/01/2021 Elaboración de Casos de Prueba.
7 | MEJ | Indicadores para garantizados |  | Ambas |  | Ederson Montesinos | Ederson Montesinos | Medio | Magali | 100% | 100% | 8 | 8 | #REF! | #REF! | #REF! | 0

## PROY19
Nº | Caso de prueba | Pre-requisites | Steps | Resultado esperado
1 | Successful login for valid user | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "standard_user" - Password: "secret_sauce" | 1. Enter a valid username 2. Enter a valid password 3. Click on Login button | The ecommerce landing page is displayed(header and footer page). Six products are displayed in the middle.
2 | Successful login for valid user pressing Enter key | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "standard_user" - Password: "secret_sauce" | 1. Enter a valid username 2. Enter a valid password 3. Press Enter | The ecommerce landing page is displayed(header and footer page). Six products are displayed in the middle.
3 | Successful login for invalid user | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "problem_user" - Password: "secret_sauce" | 1. Enter an invalid username 2. Enter a valid password 3. Click on Login button | The ecommerce landing page is displayed(header and footer page). Six identical images of products are displayed in the middle.
4 | Successful login due to slow loading | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "performance_glitch_user" - Password: "secret_sauce" | 1. Enter a performance glitch username 2. Enter a valid password 3. Click on Login button | The ecommerce landing page is displayed(header and footer page). Six products are displayed in the middle.
5 | Successful login in different sessions | 1. Go to "https://www.saucedemo.com/" 2. Chrome and Firefox browser are opened 3. Use this credentials: - Username: "standard_user" - Password: "secret_sauce" | 1. Enter a valid username in Chrome 2. Enter a valid password in Chrome 3. Click on Login button 4. Enter a valid username in Firefox 5. Enter a valid password in Firefox 6. Click on Login button | The ecommerce landing page is displayed in Chrome and Firefox browser.
6 | Verify alert "Username is required" | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Password: "secret_sauce" | 1. Enter a valid password 2. Click on Login button | An alert message is displayed "Epic sadface: Username is required" above Login button.
7 | Verify alert "Password is required" | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "standard_user" | 1. Enter a valid username 2. Click on Login button | An alert message is displayed "Epic sadface: Password is required" above Login button.
8 | Verify welcome landing page after login | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "standard_user" - Password: "secret_sauce" | 1. Enter a valid username 2. Enter a valid password 3. Click on Login button | The ecommerce landing page is displayed(header and footer page). Six products are displayed in the middle.
9 | Failed login by entering unregistered user | 1. Go to "https://www.saucedemo.com/" 2. Use un unregistered username 3. Use the next password "secret_sauce" | 1. Enter an unregistered username 2. Enter a valid password 3. Click on Login button | An alert message is displayed "Epic sadface: Username and password do not match any user in this service" above Login button.
10 | Failed login by entering invalid password | 1. Go to "https://www.saucedemo.com/" 2. Use un unregistered password 3. Use the next username "standard_user" | 1. Enter a valid username 2. Enter an unregistered password 3. Click on Login button | An alert message is displayed "Epic sadface: Username and password do not match any user in this service" above Login button.
11 | Failed login by entering blank fields | 1. Go to "https://www.saucedemo.com/" | Click on Login button | An alert message is displayed "Epic sadface: Username is required" above Login button.
12 | Failed login for locked out user | 1. Go to "https://www.saucedemo.com/" 2. Use this credentials: - Username: "locked_out_user" - Password: "secret_sauce" | 1. Enter a locked out username 2. Enter a valid password 3. Click on Login button | An alert message is displayed "Epic sadface: Sorry, this user has been locked out." above Login button.
13 | Failed login due to server failure | 1. Go to "https://www.saucedemo.com/" 2. The service is paused 3. Use this credentials: - Username: "standard_user" - Password: "secret_sauce" | 1. Enter a valid username 2. Enter a valid password 3. Click on Login button | An error web page is displayed with an image in the font: "Error 404".